## Sheet1
| jour | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
| Sommaire effort restant | 158 | 153 | 153 | 145 | 135 | 125 | 110 | 108 | 104 | 104 | 104 | 104 | 100 | 100 | 100 | 100 | 80 | 63 | 34 | 10 | 0 | 0
| Sommaire efforts dépensé | 5 | 0 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint 2. Ajout de l’aspect réalisme
Numéro cas d'utilisation |  | jours du sprint / (effort restant estimé en début de journée ¦ heures travaillées ce jour)
| Cas d'utilisation ou user-story/tâche | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 | 12 | 13 | 14 | 15 | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 | 22
|  | 158 | 158 | 5 | 153 | 0 | 153 | 8 | 145 | 10 | 135 |  | 125 |  | 110 |  | 108 |  | 104 |  | 104 |  | 104 | 104 | 100 | 100 | 100 | 100 |  | 80 |  | 63 |  | 34 |  | 10 |  | 0 | 0
10 | Implémentation des cibles
| Afficher des cibles sur le mur du sandbox | 20 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 |  | 20 |  | 20 |  | 20 |  | 20 |  | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 5 | 5 | 3 | 2 | 2 | 0 |  | 0 | 0
| Détecter le toucher de la cible par le joueur | 24 | 24 | 0 | 24 | 0 | 24 | 0 | 24 | 0 | 24 |  | 24 |  | 24 |  | 24 |  | 24 |  | 24 |  | 24 | 24 | 20 | 20 | 20 | 20 |  | 20 |  | 20 | 8 | 12 | 10 | 2 | 2 | 0 | 0
| Accumuler le pointage du joueur | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 |  | 10 |  | 10 | 2 | 8 | 8 | 0 | 0
11 | Ajout de textures à l'environnement
| Ajouter un aspect réaliste à l'environnement de tir | 30 | 30 | 5 | 25 | 0 | 25 | 8 | 17 | 10 | 7 |  | 7 | 7 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
| Fermer complètement l'espace du sandbox | 20 | 20 | 0 | 20 | 0 | 20 | 0 | 20 |  | 20 | 10 | 10 | 8 | 2 | 2 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
| Tester l'aspect hermétique de l'environnement | 4 | 4 | 0 | 4 | 0 | 4 | 0 | 4 |  | 4 |  | 4 |  | 4 |  | 4 | 4 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
12 | Effet de tir sur les armes
| Implémenter un recul réaliste pour l'arme utilisé | 4 | 4 | 0 | 4 | 0 | 4 | 0 | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 |  | 4 | 4 | 0 |  | 0 |  | 0 |  | 0 | 0
| Synchroniser le recul de l'arme avec la mire du fusil | 18 | 18 | 0 | 18 | 0 | 18 | 0 | 18 |  | 18 |  | 18 |  | 18 |  | 18 |  | 18 |  | 18 |  | 18 | 18 | 18 | 18 | 18 | 18 | 10 | 8 | 8 | 0 |  | 0 |  | 0 |  | 0 | 0
| Ajouter une imprécision sur l'arme lors de tir en rafale | 12 | 12 | 0 | 12 | 0 | 12 | 0 | 12 |  | 12 |  | 12 |  | 12 |  | 12 |  | 12 |  | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 |  | 12 | 8 | 4 | 4 | 0 |  | 0 | 0
13 | Implémenter le menu du jeu
| Chercher les gabarit possible pour le menu du jeu | 6 | 6 | 0 | 6 | 0 | 6 | 0 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 | 6 | 6 | 6 | 6 | 6 |  | 6 |  | 6 | 6 | 0 |  | 0 |  | 0 | 0
| Personnaliser le gabbarit au jeu Alpha Strike | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 |  | 10 | 4 | 6 | 6 | 0 |  | 0 | 0
État du sprint backlog après jour 3 (fin du jour 3, début du jour 4)
traduit de http://agilesoftwaredevelopment.com/scrum/simple-sprint-backlog fait par Artem Marchenko
basé sur: | http://agilesoftwaredevelopment.com/scrum/simple-sprint-backlog
Note on C6: sprint goal
Note on D10: Estimation initiale
Note on E10: Pour chaque jour, la première colonne indique le temps restant, et la deuxième colonne indique le temps travaillé sur cette tâche ce jour là. Normalement, la première colonne du jour J est égal à la différence entre la première colonne du jour J-1 (estimation en temps restant, en date du jour J-1) et de l'effort passé sur la tâche le jour J-1. Sauf si on s'est trompé d'estomation au jour J-1, auquel cas la première colonne du jour J est plus grande (on a sous-estimé) ou plus petite (on a surestimé) l'effort requis par la tâche
Note on U10: Effort left went up after some new work has been discovered
Note on B11: Id of the story. To simplify linking to the product backlog
Note on C11: User story being implemented. See http://agilesoftwaredevelopment.com/scrum/simple-product-backlog
Note on C13: Task description are written in the language that team likes. It does not have to be management understandable or "correct". In this case the accurate description would be something like "Implement reading the provider's data directory on the server side", however, team decide to make it just "Read provider's data directory", because it was simpler and everybody on the team perfectly understood what this task was about
Note on D14: The team tries not have tasks bigger, than 16 ideal engineering hours. If they happen to have a bigger task, they try to split it into two smaller and more managable ones
Note on E14: The team tries not have tasks bigger, than 16 ideal engineering hours. If they happen to have a bigger task, they try to split it into two smaller and more managable ones
Note on C46: See for reference and comments. Feel free to remove the link, though it would be very kind of you to leave it somewhere on the sheet